## Slide 1: Project Status Report
DATE: December 31, 2021

## Slide 2: Project Overall Status
Projects | Status | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan 22 | Dec 22 | Slide Number
LifeLearn Unified Sales Tool 2021 | Late |  |  |  |  |  |  |  |  |  |  |  |  | 3
ClientEd Integration into PIMS 2021 (Sprint 1 & 2) | Deployment in Progress |  |  |  |  |  |  |  |  |  |  |  |  | 4
PetNurse New Model (Phase 1) | Late |  |  |  |  |  |  |  |  |  |  |  |  | 5
WebDVM CMS Redesign 2021 | On Track |  |  |  |  |  |  |  |  |  |  |  |  | 6
Project Neuron (formerly "Consolidated Dashboard") | On Track |  |  |  |  |  |  |  |  |  |  |  |  | 7
PriceBook Project | On Track |  |  |  |  |  |  |  |  |  |  |  |  | 8
Please note that the charts in green are the original estimates and the ones in purple are the adjusted timelines for the late projects

## Slide 3
Project No. and Title: PR00771 LifeLearn Unified Sales Tool 2021
Project Sponsor: Heather Fox
Financial Category: OPEX
Current Status:
Project: Late
The design of the requested changes done, and the design is currently being reviewed, to be shared with Barking Dogs once aligned with sales
The sales demo, training kit development and upload into Litmos in progress
Due to the Change Requests during the UAT leading to some rework, target go-live date will be late January.
Project Scope:
The solution will be built in HTML and will be interactive
The contents will be presented in a non-linear, succinct format to provide flexibility with presentation styles and to customize a presentation depending on the product (PS & IS)
The content will be supported with engaging graphic and videos
Next Steps:
Required rework and bug fixing - Barking Dogs
Embed the pricing page – LL Dev
Complete the training kit development and sales training– Shannon
Complete the design review of the requested change scope and align the design with Shannon – Desmond
Budget +/- 10% | Internal - $35,893.00 External - $23,212.50
Actuals to date | Internal - $39,533.53 External - $3,565.00
Estimate to Complete | External - $19,647.50
Variance | Internal - -$3,640.53
Baseline Estimate | 835
Actual Hours Used | 657 (572 + 85)
Estimate to Complete | 178
Variance | 
Budget | 
Schedule | 
Scope | 
Overall Status | 
1. | Timely completion and signoff of UAT.
2. | Major Change Requests post-development
3. | Excess review time
4. | 
Milestone | Date | Status
Kick-off | March 8 | Completed
Detailed Project Schedule | March 9 | Completed
Complete Info Arch, Wireframes, Contents, Storyboards (Written & Visual) and Graphic Design | July 5 | Completed
Development | August 3 | Completed
Milestone | Date | Status
Complete UAT | August 17 | Completed
Training | August 24 | Ongoing
Complete Deployment | August 25 | Late
Project Closure | August 26 | Late
1. | 
2. | 
Key Milestones
Change/Decision Requests
Project Financials
Project Status
Effort Est. (Hrs.)
Major Risks

## Slide 4
Project No. and Title: PR00782 ClientEd Integration into PIMS 2021
Project Sponsor: Dr. David Goodnight
Financial Category: CAPEX
Current Status:
Project On-Track
Vetter software integration completed, and the go-live activities are in progress
HIPPO 2.0 release delayed due to new bug fixing activities at HIPPO – the ClientEd search feature along with the icon that redirect HIPPO users to ClientEd landing page, to make subscriptions have been included in HIPPO 2.0
ClientEd API integration on NaVetor PIMS is in progress, go-live rescheduled for January
Project Scope (Sprint 1 & 2):
Integrations and referral agreements with HIPPO
Develop the URL for the HIPPO PIMS to host the ClientEd icon from their platform.
Develop a ClientEd landing page that opens upon clicking the icon.
Develop the ability for new customers to subscribe or sign-in through the landing page.
Develop the ability to email and text articles from within the search window (I.e., use ClientEd the usual way after signing in).
Upgrade the API for all PIMS use
Next Steps:
Continue to work with NaVetor, HIPPO & Vetter on their release and marketing communication plan – Kaityln & Erick
Continue to work with NaVetor & HIPPO technical team on the ClientEd API integration- Steve & Emily
Budget +/- 50% | $49,817.00
Actuals to date | $34,151.18
Estimate to Complete | $15,665.82
Variance | 
Baseline Estimate | 820
Actual Hours Used | 596
Estimate to Complete | 224
Variance | 
Budget | 
Schedule | 
Scope | 
Overall Status | 
1. | HIPPO's readiness due to internal upgrades
2. | Delayed response from the PIMS providers (HIPPO and Navetor)
3. | 
Milestone | Date | Status
Kick-off | March 23 | Complete
Detailed Project Schedule | April 30 | Complete
Design | May 19 | Complete
Sprint 1 | June 4 | Complete
Milestone | Date | Status
Sprint 2 | July 16 | Complete
Marketing & Communication | Dependent on the Partners | Ongoing
Project Closure | Dependent on the Partners | Not Started
1. | 
2. | 
3. | 
Key Milestones
Change/Decision Requests
Project Financials
Project Status
Effort Est. (Hrs.)
Major Risks

## Slide 5
Project No. and Title: PR00780 PetNurse New Model (Consumer) 2021 – Phase 1
Project Sponsor: Dr. David Goodnight
Financial Category: CAPEX
Current Status:
Project Late
UAT is in progress
Rework and bug fixing are also in progress
QA retesting is also in progress
  155 tickets raised: 122 closed, 33 open (this includes 5 major issues)
End to End test with VetConnections done, but a critical error was encountered, to be fixed by LL dev
Deployment plan has been developed, review is in process
Planned marketing tasks for this Phase completed (Social media account, GMB and UTM creation)
Project Scope:
Host the PetNurse smart icon on the veterinary website.
Add the Smart Icon to the output of Pet Health Checker as a way for clients to speak to a live person.
The PetNurse website to include Educational and marketing content, eCommerce capability to accept payments from pet owners and other features
Next Steps:
QA testing sign-off – Mandeep (Late)
Develop Phase 2 SDD – Dustin
UAT sign-off – David, Mark, Erick
Deploy Phase 1 to production – Dustin
Budget +/- 50% | $67,682.00
Actuals to date | $111,720.55
Estimate to Complete | 
Variance | -$44,038.55
Baseline Estimate | 1183
Actual Hours Used | 2064
Estimate to Complete | 
Variance | -881
Budget | 
Schedule | 
Scope | 
Overall Status | 
1. | Data security when sending call details to a referring hospital – Vet Connection to Hospitals
2. | Constraint in development resource availability
3. | Redesign leading to significant rework
Milestone | Date | Status
Kick-off | April 6 | Completed
Detailed Project Schedule Draft | April 9 | Completed
Phase 1 BRD & Design | May 11 | Completed
Complete Phase 1 Development | August 25 | Completed
Complete Phase 1 QA Testing | September 16 | Ongoing
Milestone | Date | Status
Complete UAT | September 23 | Ongoing
Marketing Tasks | September 29 | Completed
Complete Deployment | October 1 | Ongoing
Complete Phase 2 Planning | December 31 | Ongoing
1. | 
2. | 
3. | 
Key Milestones
Change/Decision Requests
Project Financials
Project Status
Effort Est. (Hrs.)
Major Risks

## Slide 6
Project No. and Title: PR00778 WebDVM CMS Redesign 2021
Project Sponsor: Keith Washington
Financial Category: CAPEX
Current Status:
Project On-Track
At 86% time gone, the entire project is about 86% complete
QA testing ongoing:
  95 tickets raised: 94 closed, 1 open
  Regression testing is in progress
UAT testing is in progress
Project Scope:
Redesign product dashboard to improve user experience and feature
Redesign content/post editor to improve user experience and simplify tools to ease client self-serve usage
Add standard page templates to page editor and rollout platform wide – eliminating client admin access to advanced tools and improving design ability to simplify internal page creation while improving variety
Next Steps:
Provide the QA sign off - Mandeep
Complete the UAT – Dale, Stefano & Amie
Budget +/- 10% | $96,076.25
Actuals to date | $75,400.43
Estimate to Complete | $20,675.82
Variance | 
Baseline Estimate (Internal) | 1806
Actual Hours Used (Internal) | 1401
Estimate to Complete | 405
Variance | 
Budget | 
Schedule | 
Scope | 
Overall Status | 
1. | 
2. | 
3. | 
Milestone | Date | Status
Kick-off | May 7 | Completed
Draft detailed Project Schedule | May 26 | Completed
Planning & Schedule update | June 28 | Completed
Complete Development | November 4 | Completed
Complete QA | January 4 | On Track
Milestone | Date | Status
Complete UAT | Jan 19, 2022 | On Track
Communication | Jan 25, 2022 | Not Started
Complete Deployment | Jan 25, 2022 | Not Started
Project Closure | Jan 28, 2022 | Not Started
1. | 
2. | 
3. | 
Key Milestones
Change/Decision Requests
Project Financials
Project Status
Effort Est. (Hrs.)
Major Risks

## Slide 7
Project No. and Title: Project Neuron
Project Sponsor: Keith Washington
Financial Category: CAPEX
Current Status:
Project On-Track
First sprint starts on January 4
Project Scope:
Dashboard to provide analytics on all products and customers from all verticals, accessible internally and externally (with the required authentication and authorization)
SSO to access all products across the 4 verticals
Products in scope are:
    Websites - WebDVM, PS Vet, CPASS, PS Dental, PS Legal, Nifty
    Social Media Management
    ClientEd
    Sofie
    Digital Services - PPC, Social Ads, CallRail/Call Tracking, SEO, Link Strategies & Video Marketing
    Client Communication Software - ALLYDVM, PracticeMojo, Telemedicine/Teletriage, PetNurse, Petriage
Next Steps:
Continue to refine the user stories and acceptance criteria – Dale
Continue to prioritize the User Stories – Dale
Start development – all team members
Budget +/- 50% | 
Actuals to date | $8,398
Estimate to Complete | 
Variance | 
Baseline Estimate (Internal) | 
Actual Hours Used (Internal) | 127
Estimate to Complete | 
Variance | 
Budget | 
Schedule | 
Scope | 
Overall Status | 
1. | Resource Availability
2. | Prompt decision on collaboration tool and other technologies to be used
3. | 
Milestone | Date | Status
Kick-off | Nov 22 | Completed
Project Release Plan | Dec 17, 2022 | Completed
Sprint 1 | Feb 1, 2022 | Not Started
Sprint 2 | Mar 1, 2022 | Not Started
Sprint 3 | Mar 29, 2022 | Not Started
Milestone | Date | Status
Sprint 4 | Apr 26 | Not Started
Sprint 5 | May 24 | Not Started
Sprint 6 | Jun 21 | Not Started
Project Closure | TBD | Not Started
1. | Decision on the technical solution to be used for this project (analytics, SSO) – Bob, Steve, Cody, Tony
2. | 
3. | 
Key Milestones
Change/Decision Requests
Project Financials
Project Status
Effort Est. (Hrs.)
Major Risks

## Slide 8
Project No. and Title: PriceBook Project
Project Sponsor: Keith Washington
Financial Category: OPEX
Current Status:
Project On-Track
Development activities started to enable MVP of the project ready for VMX in mid-January
  Test product rate plan created in Zuora sandbox
  Endpoint creation ongoing
  API documentation in progress
Requirement gathering and BRD documentation ongoing
Project Scope:
Add all ProSites Vet products to the LifeLearn SalesForce Pricebook and provision them in Zoura
Implementation of a data integration to transfer closed/won information from LifeLearn SalesForce to ProSites SalesForce
Next Steps:
Develop the BRD – Hemant (Jan 14)
Complete the endpoint creation – Anand & Cody (ASAP)
Complete the API documentation – Anand (ASAP)
Budget +/- 50% | 
Actuals to date | $2,755
Estimate to Complete | 
Variance | 
Baseline Estimate (Internal) | 
Actual Hours Used (Internal) | 45
Estimate to Complete | 
Variance | 
Budget | 
Schedule | 
Scope | 
Overall Status | 
1. | Resource availability from finance to work on the project
2. | 
3. | 
Milestone | Date | Status
Kick-off | Dec 7 | Completed
Draft Project Schedule | Dec 13 | Completed
BRD Review & Approval | Jan 20 | Ongoing
Development | Jan 5 | Not Started
QA Testing | Jan 10 | Not Started
Milestone | Date | Status
UAT | Jan 13 | Not Started
Marketing, Training & Communication | Jan 13 | Not Started
Deployment (MVP) | Jan 14 | Not Started
Project Closure | TBD | Not Started
1. | 
2. | 
3. | 
Key Milestones
Change/Decision Requests
Project Financials
Project Status
Effort Est. (Hrs.)
Major Risks

## Slide 9
Project(s) to be kicked off in the coming weeks

## Slide 10: Project(s) on hold
Practice Solutions Phased Pricing
Sofie Differential Diagnostic Generator 2021
Transfer Wizard
ClientEd Portal and Security

## Slide 11
Project No. and Title: PR00838 2021 Practice Solutions Phased Pricing 2021
Project Sponsor: Keith Washington
Financial Category: OPEX
Current Status:
Project On-Track
The 1st draft of the BRD (Phase 1B) is complete
Further review required by the product team on the LifeLearn pricing alignment with ProSites and the recommended strategy
Review of key tasks and BRD approval this coming week
Project Scope:
Update the pricing for WebDVM, Sofie, and ClientEd customers and prospects in 5 phases:
  Phase 1b - Rollout New Rate Plans for New Sales [1, 2, 3, 4]
  Phase 2 - Sofie Existing Clients Migration [5]
  Phase 3 - ClientEd Existing Clients Migration [6]
  Phase 4 - WebDVM Existing Client Migration – Current Editions (Core, Plus, Pro) [7]
  Phase 5 - WebDVM Existing Client Migration – Legacy Editions (Essential, Standard, Premium, Exclusive) [8]
This includes
  All clients on current product editions
  Maximum single discount per client (excluding promotional termed discounts)
  All clients located in Canada paying new CAD pricing
  Majority of clients on a monthly subscription
Next Steps:
BRD Approval – All Approvers
Zuora Sandbox testing – Hemant
Marketing assets - Marketing
Budget +/- 50% | $87,785
Actuals to date | $2,789.
Estimate to Complete | $84,996.
Variance | 
Baseline Estimate (Internal) | 1238
Actual Hours Used (Internal) | 52
Estimate to Complete | 1186
Variance | 
Budget | 
Schedule | 
Scope | 
Overall Status | 
1. | Resource Availability
2. | 
3. | 
1. | 
2. | 
3. | 
Key Milestones
Change/Decision Requests
Project Financials
Project Status
Effort Est. (Hrs.)
Major Risks
Milestone | Date | Status
Kick-off | August 11 | Complete
Draft detailed Project Schedule | August 31 | Complete
BRD Completion and Approval | Sept 14 | In Progress
Marketing Assets Completion and Approval | Sept 14 | Not Started
Pricing in Quora sandbox | Sept 22 | Not Started
Milestone | Date | Status
Complete UAT | Sept 29 | Not Started
Communication | Sept 17 | Not Started
Complete Deployment | Oct 1 | Not Started
Project Closure | Oct 8 | Not Started
ON HOLD

## Slide 12: Projects canceled
N/A

## Slide 13: Thank You